## Task4.1P
Hour starting | Burned Down | Balance |  | Hourly Completed
| Planned | Planned | Actual
9:00 | 10 | 30 | 30 | 12
10:00 | 10 | 20 | 18 | 9
11:00 | 10 | 10 | 9 | 5
12:00 | 0 | 0 | 4
Use this sheet as a template for your Doubtfire tasks. You can modify according to your task requirements.

## TaskDemo
Hour starting | Burned Down | Balance |  | Hourly Completed
| Planned | Planned | Actual
9:00 | 10 | 30 | 30 | 10
10:00 | 10 | 20 | 20 | 10
11:00 | 10 | 10 | 10 | 3
12:00 | 0 | 0 | 7 | 0

## SprintDemo
Date | Burned Down | Balance |  | Daily Completed
| Planned | Planned | Actual
2014-05-12 | 12 | 120 | 120 | 15
2014-05-13 | 12 | 108 | 105 | 10
2014-05-14 | 12 | 96 | 95 | 12
2014-05-15 | 12 | 84 | 83 | 1
2014-05-16 | 12 | 72 | 82 | 1
2014-05-19 | 12 | 60 | 81 | 22
2014-05-20 | 12 | 48 | 59 | 15
2014-05-21 | 12 | 36 | 44 | 16
2014-05-22 | 12 | 24 | 28 | 13
2014-05-23 | 12 | 12 | 15 | 14
2014-05-24 | 0 | 0 | 1 | NA

## sprint
Date | Burned Down | Balance |  | Daily Completed
| Planned | Planned | Actual
2019-07-22 | 10 | 100 | 100 | 15
2019-07-23 | 10 | 90 | 85 | 10
2019-07-24 | 10 | 80 | 75 | 12
2019-07-25 | 10 | 70 | 63 | 1
2019-07-26 | 10 | 60 | 62 | 1
2019-07-27 | 10 | 50 | 61 | 22
2019-07-28 | 10 | 40 | 39 | 15
2019-07-29 | 10 | 30 | 24 | 16
2019-07-30 | 10 | 20 | 8 | 5
2019-07-31 | 10 | 10 | 3 | 3
2019-08-01 | 0 | 0 | 0 | NA